## Overview
HORO Bootstrapped Launch System
30-day launch calendar, WhatsApp scripts, and a first-100-customers tracker built for a no-ads MVP.
Working assumptions |  | Launch dashboard
Category: artist-led wearable-art / identity-expression tees | Content days complete
Primary beachhead: Cairo-based portrait-aesthetic gift buyers reached through artist audiences and social commerce | Planned content days
Price architecture: core EGP 599-649; limited artist drops EGP 799-899 | Leads in tracker
Primary channels: Instagram, TikTok, WhatsApp, one simple website/catalog, small popups | Confirmed orders
Internal mantra: Wear and Share Identity Through Art | Delivered orders
Avg order value (EGP)
Lead-to-order rate
How to use this workbook | Delivery success rate
1) Work from the 30-Day Calendar sheet each day. Change Status as work is completed.
2) Use the Scripts sheet for WhatsApp, COD confirmation, delivery issues, and sizing messages.
3) Add every real lead to the First 100 Tracker, even if they do not order.
4) Watch the Overview sheet for lead-to-order rate, delivery success rate, and average order value.
5) Do not discount the tee by default; use urgency, gifting add-ons, and artist story instead.
Research basis
Built from the HORO market-research documents uploaded in this chat: wearable-art positioning, gifting priority, artist-collaboration tests, social-commerce/COD reality, and small-batch launch economics.

## 30-Day Calendar
30-Day Organic Launch Calendar
Goal: get the first 100 orders with artist content, WhatsApp conversion, gifting hooks, and one tight popup loop.
Day | Phase | Goal | Primary content | Angle / hook | Channel | CTA | Owner | Status | KPI to watch
1 | Prep | Open waitlist | Founder intro Reel + why HORO exists | Identity + gifting | IG Reels / TikTok | Join WhatsApp waitlist | Founder | Planned | Waitlist joins
2 | Prep | Set visual standard | Print close-up carousel | Quality proof | IG | Save / DM size | Founder | Planned | Saves
3 | Prep | Introduce artist 1 | Artist studio clip | Real collaborator, not stock design | IG Stories + Reel | Follow artist + join list | Artist | Planned | Profile visits
4 | Prep | Introduce artist 2 | Artist hand sketch / screen recording | Art becoming wearable | IG / TikTok | Comment favorite piece | Artist | Planned | Comments
5 | Prep | Build trust | Fabric + fit video | Feels good on fabric, not sticker print | IG Reel | Ask for size help on WhatsApp | Founder | Planned | WhatsApp messages
6 | Prep | Gift hook | Birthday / graduation mock gift post | More personal than generic tees | IG / FB | Send to a friend | Founder | Planned | Shares
7 | Prep | Warm audience | Stories poll: which drop first? | Audience co-creation without custom printing | IG Stories | Vote + join list | Founder | Planned | Poll votes
8 | Launch | Reveal drop | Hero Reel with top 3 artworks | Curated, not crowded | IG Reel / TikTok | Shop / DM now | Founder | Planned | Site visits
9 | Launch | Push artist credibility | Artist explains one piece on video | Why this artwork matters | IG Reel | Reserve piece | Artist | Planned | DMs
10 | Launch | Push trust | Packaging + artist card video | Gift-worthy unboxing | IG Reel / Stories | Reserve gift order | Founder | Planned | Gift inquiries
11 | Launch | Handle objections | FAQ carousel | Price, fit, care, COD | IG carousel / FB | Ask anything on WhatsApp | Founder | Planned | FAQ taps
12 | Launch | Convert warm leads | WhatsApp manual follow-up day | Personal but low-pressure | WhatsApp | Confirm order | Founder | Planned | Order confirmations
13 | Launch | Social proof seed | Friends / micro-creators receive samples | Real people wearing it | IG Stories | Reply for size | Founder | Planned | Story replies
14 | Launch | Urgency | First 100 pieces counter | Limited run, no ad spend, no overproduction | IG Stories | Order before count drops | Founder | Planned | Orders
15 | Launch | Gifting push | Gift note + artist card post | Easy thoughtful gift | IG / FB | Book gift order | Founder | Planned | Gift conversions
16 | Launch | Retarget manually | Founder DMs warm non-buyers | Not spam: answer fit / shipping doubts | Instagram / WhatsApp | Complete order | Founder | Planned | Recovered leads
17 | Launch | Proof of wearability | Outfit styling reel | Artful but wearable daily | IG Reel / TikTok | Save this look | Founder | Planned | Saves
18 | Launch | Artist audience push | Artist post to own page | Borrow existing community trust | Artist IG | Tap to HORO page | Artist | Planned | New followers
19 | Launch | Popup prep | Announce mini popup / meetup | Touch, see, scan, order | IG Stories / Feed | RSVP | Founder | Planned | RSVPs
20 | Launch | Popup day | Live stories from popup | Real-world proof | IG Stories | Scan QR / order | Founder | Planned | Popup orders
21 | Launch | After-popup loop | Customer reactions montage | People get it quickly in person | IG Reel | Message for remaining stock | Founder | Planned | Inbounds
22 | Scale | Referral push | Customer repost template | Invite a friend without discounting | IG Stories / WhatsApp | Share your photo | Founder | Planned | Tagged posts
23 | Scale | Fit confidence | Model heights + sizes post | Reduce return anxiety | IG carousel | Ask size question | Founder | Planned | Size DMs
24 | Scale | Delivery trust | Courier / dispatch post | Realistic service behavior | IG Stories | Confirm COD now | Founder | Planned | Confirmed COD
25 | Scale | Occasion angle | Graduation / birthday / friend gift content | Who this is perfect for | IG / FB | Send to buyer | Founder | Planned | Shares
26 | Scale | Creator loop | Micro-creator outfit post | Taste signal without big influencer spend | IG Reels | Follow + DM | Creator | Planned | New leads
27 | Scale | Artist depth | One artwork story card post | Meaning + origin | IG carousel | Pick your artwork | Artist | Planned | Carousel completion
28 | Scale | Inventory discipline | Almost sold out story | Small batch, not fake urgency | IG Stories | Claim remaining pieces | Founder | Planned | Sell-through
29 | Scale | Collect proof | Ask for mirror photos / reviews | UGC creates next wave | WhatsApp / IG | Send photo / review | Founder | Planned | UGC count
30 | Scale | Decide next drop | Performance recap + waitlist for drop 2 | Founders share what sold | IG Stories / close friends | Join next-drop list | Founder | Planned | Next-drop waitlist

## Scripts
WhatsApp + Service Scripts
Use these as a starting point. Keep them warm, clear, and firm enough to protect time and margins.
Scenario | Best use | Script
Waitlist reply | New inbound from IG / Stories | Hi — thank you for the interest. We are launching in small batches, so I can add you to the first access list here and send size / pricing details before stock goes live.
Size help | Customer asks which size to buy | Happy to help. Send me your height, weight, and the fit you usually prefer, and I’ll suggest the clearest size before you order.
COD confirmation | Before dispatch | Thank you — your order is almost confirmed. Please reply with your full address, nearest landmark, and active phone number today so we can release it to the courier. Unconfirmed COD orders are not dispatched.
Delayed courier | Customer chasing shipment | I’m sorry this is taking longer than expected. I’ve already followed up with the courier, and I’ll send you the clearest delivery update as soon as I get the confirmed timing.
Sizing complaint | Customer says fit is wrong | I’m sorry the fit was not right. Send me your height, weight, the size you received, and one clear photo if possible, and I’ll guide the exchange step by step.
Gift order | Customer buying for someone else | We can prepare it as a gift order with the artist card and note. If you want, send me the occasion and I’ll suggest the strongest piece for that person.
Soft close after inquiry | Warm lead did not order | Just checking in in case you still want the piece. I can help with sizing or show you the remaining artworks before this batch closes.
Review request | After delivery | Hope it arrived safely. If you have a mirror photo or quick feedback, send it here — it really helps us build the next drop well.

## First 100 Tracker
First 100 Customers Tracker
Add every real lead. The goal is to learn which artist, hook, and channel actually convert without ad spend.
Lead ID | Date added | Name / handle | Source channel | Artist / collection | Segment | Stage | Order value (EGP) | Payment | Delivery status | Follow-up date | Owner | Notes
1 | [5 empty] | Lead | 0
2 | [5 empty] | Lead | 0
3 | [5 empty] | Lead | 0
4 | [5 empty] | Lead | 0
5 | [5 empty] | Lead | 0
6 | [5 empty] | Lead | 0
7 | [5 empty] | Lead | 0
8 | [5 empty] | Lead | 0
9 | [5 empty] | Lead | 0
10 | [5 empty] | Lead | 0
11 | [5 empty] | Lead | 0
12 | [5 empty] | Lead | 0
13 | [5 empty] | Lead | 0
14 | [5 empty] | Lead | 0
15 | [5 empty] | Lead | 0
16 | [5 empty] | Lead | 0
17 | [5 empty] | Lead | 0
18 | [5 empty] | Lead | 0
19 | [5 empty] | Lead | 0
20 | [5 empty] | Lead | 0
21 | [5 empty] | Lead | 0
22 | [5 empty] | Lead | 0
23 | [5 empty] | Lead | 0
24 | [5 empty] | Lead | 0
25 | [5 empty] | Lead | 0
26 | [5 empty] | Lead | 0
27 | [5 empty] | Lead | 0
28 | [5 empty] | Lead | 0
29 | [5 empty] | Lead | 0
30 | [5 empty] | Lead | 0
31 | [5 empty] | Lead | 0
32 | [5 empty] | Lead | 0
33 | [5 empty] | Lead | 0
34 | [5 empty] | Lead | 0
35 | [5 empty] | Lead | 0
36 | [5 empty] | Lead | 0
37 | [5 empty] | Lead | 0
38 | [5 empty] | Lead | 0
39 | [5 empty] | Lead | 0
40 | [5 empty] | Lead | 0
41 | [5 empty] | Lead | 0
42 | [5 empty] | Lead | 0
43 | [5 empty] | Lead | 0
44 | [5 empty] | Lead | 0
45 | [5 empty] | Lead | 0
46 | [5 empty] | Lead | 0
47 | [5 empty] | Lead | 0
48 | [5 empty] | Lead | 0
49 | [5 empty] | Lead | 0
50 | [5 empty] | Lead | 0
51 | [5 empty] | Lead | 0
52 | [5 empty] | Lead | 0
53 | [5 empty] | Lead | 0
54 | [5 empty] | Lead | 0
55 | [5 empty] | Lead | 0
56 | [5 empty] | Lead | 0
57 | [5 empty] | Lead | 0
58 | [5 empty] | Lead | 0
59 | [5 empty] | Lead | 0
60 | [5 empty] | Lead | 0
61 | [5 empty] | Lead | 0
62 | [5 empty] | Lead | 0
63 | [5 empty] | Lead | 0
64 | [5 empty] | Lead | 0
65 | [5 empty] | Lead | 0
66 | [5 empty] | Lead | 0
67 | [5 empty] | Lead | 0
68 | [5 empty] | Lead | 0
69 | [5 empty] | Lead | 0
70 | [5 empty] | Lead | 0
71 | [5 empty] | Lead | 0
72 | [5 empty] | Lead | 0
73 | [5 empty] | Lead | 0
74 | [5 empty] | Lead | 0
75 | [5 empty] | Lead | 0
76 | [5 empty] | Lead | 0
77 | [5 empty] | Lead | 0
78 | [5 empty] | Lead | 0
79 | [5 empty] | Lead | 0
80 | [5 empty] | Lead | 0
81 | [5 empty] | Lead | 0
82 | [5 empty] | Lead | 0
83 | [5 empty] | Lead | 0
84 | [5 empty] | Lead | 0
85 | [5 empty] | Lead | 0
86 | [5 empty] | Lead | 0
87 | [5 empty] | Lead | 0
88 | [5 empty] | Lead | 0
89 | [5 empty] | Lead | 0
90 | [5 empty] | Lead | 0
91 | [5 empty] | Lead | 0
92 | [5 empty] | Lead | 0
93 | [5 empty] | Lead | 0
94 | [5 empty] | Lead | 0
95 | [5 empty] | Lead | 0
96 | [5 empty] | Lead | 0
97 | [5 empty] | Lead | 0
98 | [5 empty] | Lead | 0
99 | [5 empty] | Lead | 0
100 | [5 empty] | Lead | 0
Tip | Use Source channel and Artist / collection consistently. That is how you learn what actually moves the first 100 orders.